## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 29.05.2024 - 12:00
Team Number |  | 02_ZenMonkey
Participant 1 |  | Rafin Ifta Alam
Participant 2 |  | Lukas Huber
Participant 3 |  | Dominik Pierdiluca
Mentor |  | Helmuth Lammer
List the IDs of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | added sort option | 4 | 6 | 2 | 1
2 | added (continous) searchfuction | 7 | 6 | -1 | 1
3 | added the 'About"-site(Hilfe) (3) | 1 | 2 | 1 | 1
6 | creatring user table in db (6) | 1 | 1 | 0 |  | 1
7 | migrating db from docker to php myadmin (7) | 2 | 3 | 1 | 1
7 | connecting database to project (7) | 1 | 1 | 0 | 1
15 | creating sessions with php (15) | 5 | 3 | -2 |  | 1
17 | added the Privacy Policy site (17) | 1 | 1 | 0 | 1
16 | added the Kundenservice-site (16) | 2 | 3 | 1 | 1
9 |  |  |  | 2 | 7 | 2